## Sheet1
Project Name | UnlockCells
Name | Task/Feature | Estimated Duration
Ghibuci Andrei | Hardware Implementation | 10h
Ghibuci Andrei | Data Acquisition(client) | 12h
Ghibuci Andrei | Data send to server(client) | 12h
Trifan Filip | Front-end for server | 100h
Manea Dragos | Database tabels | 24h
Manea Dragos | Connect Database to server | 40h
Cretan Alexandru | Admin features | 40h
Cretan Alexandru | Home feature | 24h
Ghibuci Andrei | Report feature | 10h
Ghibuci Andrei | Monitor feature | 30h
Trifan Filip | Monitor feature(support) | 12h
Trifan Filip | Testing admin features | 8h
Ghibuci Andrei | Testing Hardware | 8h
Ghibuci Andrei | Testing Monitor feature | 8h
Cretan Alexandru | Testing report feature | 8h
Manea Dragos | System test | 24h